Cost Management Plan

Wireless Access for Health for Hospitals (WAH4H)

Asia Pacific College (Pseudoers BSCS-SS231 Group)

3 Humabon Place, Magallanes

Makati City, Metro Manila 1232

April 15, 2026

Table of Contents

Introduction	3

Cost Management Approach	3

Measuring Project Costs	4

Reporting Format	4

Cost Variance Response Process	4

Cost Change Control Process	5

Project Budget	5

# Introduction

The Cost Management Plan (CMP) for WAH4Hospital (WAH4H) defines how project costs will be measured, tracked, reported, and controlled throughout the project lifecycle. It establishes the standards for cost accountability and ensures that the project delivers value within its defined resource constraints.

WAH4H requires a production-ready cloud deployment to transition from a localized academic build to a live, usable system. The project operates on an 8-week MVP schedule, utilizing a fixed budget for labor and management, while incurring zero infrastructure costs for the project team (all cloud hosting, Linode instances, and network management are wholly funded and managed by WAH).

The project is divided into the following phases:

- Initiating: 03/11/2026 – 03/27/2026

- Planning: 03/30/2026 – 04/14/2026

- Executing: 04/15/2026 – 05/28/2026

- Closing: 05/29/2026 – 06/09/2026

The Project Manager is responsible for managing and reporting on project costs, while the Cost/Budget Analyst computes the Sprint Earned Value Management (EVM) metrics.

# Cost Management Approach

Costs for WAH4H will be managed at the Work Package level within the Work Breakdown Structure (WBS), aligned with the sprint-based delivery structure. Each sprint is treated as a Control Account (CA) for EVM purposes.

The following rules govern cost management:

- Total Budget: Budget at Completion (BAC) is fixed at $85,400.00.

- Infrastructure Costs: $0.00 (Funded entirely by the WAH infrastructure allocation).

- EVM Measurement Level: Sprint / Control Account level; EVM computed at the end of each sprint cycle.

- Reporting Frequency: EVM metrics (PV, EV, AC, CV, SV, CPI, SPI) are computed and reported after each sprint review.

Cost variances are tracked using a traffic-light system. Yellow status (cautionary) triggers a written explanation from the Project Manager. Red status (alert) triggers a formal Corrective Action Plan requiring approval before proceeding.

# Measuring Project Costs

WAH4H uses Earned Value Management (EVM) to measure cost and schedule performance per sprint. The performance indexes are evaluated against the following thresholds:

| Performance Measure | Yellow | Red |
| --- | --- | --- |
| Schedule Performance Index (SPI) | Between 0.8 and 0.9 OR between 1.1 and 1.2 | Less than 0.8 OR greater than 1.2 |
| Cost Performance Index (CPI) | Between 0.8 and 0.9 OR between 1.1 and 1.2 | Less than 0.8 OR greater than 1.2 |

If the SPI or CPI enters Yellow status, the Project Manager must document the reason in the sprint status report. If either index enters Red status, a formal Cost Variance Corrective Action Plan must be presented.

# Reporting Format

Cost management reporting for WAH4H is included in the Sprint Status Report generated after each sprint review. The Cost Management section contains:

- Current Planned Value (PV), Earned Value (EV), and Actual Cost (AC) values for the sprint and cumulative project totals.

- Computed Schedule Variance (SV), Cost Variance (CV), SPI, and CPI values with traffic-light status indicators.

- Explanation of any cost or schedule variances outside acceptable thresholds.

- Change requests triggered by cost overruns or schedule delays, if applicable.

Reports are maintained in the project's tracking software and document repository. The Project Manager presents cost performance results to the Project Sponsor and Faculty Adviser at required intervals.

# Cost Variance Response Process

The control thresholds for WAH4H are an SPI or CPI of less than 0.8 or greater than 1.2. If either threshold is triggered, the following response process applies:

- The Project Manager identifies and documents the cost variance in the sprint status report within 2 business days of detection.

- The Project Manager presents corrective action options (e.g., schedule acceleration, scope adjustment) within 5 business days.

- The Faculty Adviser and/or Project Sponsor selects a corrective action.

- The Project Manager prepares and presents a formal Cost Variance Corrective Action Plan within 3 business days of direction.

- Upon approval, the Corrective Action Plan is incorporated into the project plan and tracking software is updated.

# Cost Change Control Process

Any change to the project budget or cost baseline must follow the project's formal change request process. Budget changes require approval from the Project Sponsor (Pey Canlas) and Faculty Adviser before implementation.

The Project Manager is responsible for submitting and tracking all cost-related change requests. Because infrastructure is handled externally by WAH, internal cost changes will primarily be triggered by authorized adjustments to the MVP scope or required schedule extensions requiring additional labor tracking.

# Project Budget

The budget for the WAH4H project is established to cover the labor and project management efforts required to execute the 8-week MVP deployment pipeline (Local, Sandbox, Production).

Total Project Budget Summary:

- Initiation Phase: $42,000.00

- Planning Phase: $43,400.00

- Infrastructure Costs (Linode/Akamai): $0.00 (Managed by WAH)

- Tooling Costs: $0.00 (Free tiers / WAH provided)

- Total Project Budget (BAC): $85,400.00

(Note: While the Initiation and Planning phases establish the financial baseline of $85,400.00, performance is actively managed against the EVM metrics through the Executing and Closing phases to forecast the Estimate at Completion).

Sponsor Acceptance

Approved by the Project Sponsor:

Date:

Pey Canlas

Executive Director